## 1. Evidence reviewed
Source | Evidence | Insight
GitHub repository | csdmichael/fleet-inspection-and-maintenance, default branch main | A working repository and a protected delivery baseline should be treated as the improvement target.
GitHub pull requests | PR #2 and PR #3 are merged; PR #1 remains open from 24 Aug 2026 | Delivery activity has occurred, but the outstanding older PR needs disposition to avoid a divergent/stale implementation path.
GitHub Actions | Active CI and Deploy to Azure workflows | CI and deployment workflow assets exist. Improvement should focus on enforceable quality and release evidence rather than introducing a second pipeline.
Azure DevOps | Existing automated-validation suite #713 is In Progress; related test cases #881–#885 are in Design | Test strategy is planned but not yet demonstrated as executable, traceable release evidence.
Azure DevOps | Older planning/implementation chains such as #686–#711 are closed; a second, overlapping planning backlog #1328–#1375 remains New | There is duplicate or competing work-item decomposition. This weakens delivery reporting and requirements-to-test traceability.
Intake and approved requirements summary | Critical defect grounding, immutable inspections/evidence, offline capture, controlled release, workshop notification, usage-based service planning, and human-reviewed AI classification are required capabilities | The improvement priority must remain safety- and evidence-critical flows, not new functional scope.

## I-02 — Turn the existing tes
Validation area | Required scenarios
Guided inspection | Applicable checklist loads for the selected vehicle; odometer is collected before the checklist; every required item receives an outcome; failed items cannot proceed without required description and evidence.
Immutable evidence | Submitted inspection records retain driver, vehicle, capture time, odometer, checklist version, item outcomes, and evidence references; update/delete attempts are rejected or audited according to the approved retention model.
Grounding | A critical defect causes the authoritative grounding workflow; the client shows a persistent do-not-drive state; trip start is refused while grounding/release state forbids it.
Integration failure | If authoritative grounding cannot be confirmed, the driver remains instructed not to drive, the failure is recorded, retry is scheduled, and the required escalation path is observable.
Notification | Workshop and duty-management notification attempts capture channel, timestamp, outcome, fallback behavior, and final escalation outcome.
Repair and release | Repair evidence is recorded; only a correctly authorized competent person can release; release is auditable; trip start remains blocked until release succeeds.
Offline synchronization | Offline inspection data preserves original capture time, synchronizes idempotently after connectivity returns, does not create duplicates, and exposes conflict/failure status to the user.
Accessibility | The grounding state, validation errors, checklist progress, and notification status remain perceivable without reliance on colour or device-specific interaction.

## 4. Proposed implementation s
Order | Change | Dependency
1 | Approve the authoritative work-item hierarchy and close/link duplicates | None
2 | Resolve the database architecture decision | Required before persistence, migration, or production-like evidence work
3 | Map existing implementation PRs and code areas to authoritative stories | Authoritative hierarchy
4 | Make the existing validation suite executable and publish CI evidence | Story mapping
5 | Implement critical-path CI gates for grounding, trip blocking, evidence integrity, release, and offline idempotency | Executable tests
6 | Add reconciliation and integration-failure observability | Approved configuration and integration contracts
7 | Complete authorization and evidence-retention verification | Approved roles and retention policy
8 | Triage the stale PR and conduct Dev release-readiness review | Current CI gates and traceability