## Slide 1: Delivery Insights
Fleet Inspection And Maintenance
Agentic SDLC Factory · October 03, 2026

## Slide 2: Insights Agent — Improve-Stage Proposal
Project: Fleet Inspection And Maintenance Target environment: Dev Status: Review required — no changes made Assessment date: 03 October 2026

## Slide 3: 1. Evidence reviewed
The supplied intake documents are marked Draft and the available text is truncated in places. The approved requirements-agent proposal also records this limitation. Consequently, this proposal does not redefine busine…

## Slide 4: 2. Improvement objective
Establish a single, reviewable Dev release-evidence path proving that the implemented system preserves the safety-critical and compliance-critical requirements:
a critical defect cannot result in a drivable vehicle;
inspection records and evidence remain immutable and attributable;
offline capture is neither lost nor duplicated when synchronized;
repairs cannot return a vehicle to service without an authorized release;
failed integrations produce an observable, actionable fallback and escalation outcome.
This proposal deliberately excludes new product features, new analytics, or changes to the agreed user experience.

## Slide 5: 3. Findings and recommended changes
Finding: Closed work-item chains exist for implemented capability areas, while a second set of overlapping New stories and tasks remains in Azure DevOps. Examples include closed grounding and workshop chains #695–#702…
Risk: Teams may implement or test the same requirement twice, report incorrect completion status, or attach release evidence to the wrong work item.
Proposed change:
Select one authoritative hierarchy under the existing Fleet Inspection And Maintenance epic.
For every duplicate New item:
link it to the completed equivalent where it is genuinely superseded;
close it as duplicate, or retain it only where it defines a distinct, currently unimplemented gap;

## Slide 6: 4. Proposed implementation sequence
Order | Change | Dependency
1 | Approve the authoritative work-item hierarchy and close/link duplicates | None
2 | Resolve the database architecture decision | Required before persistence, migration, or production-like evidence work
3 | Map existing implementation PRs and code areas to authoritative stories | Authoritative hierarchy
4 | Make the existing validation suite executable and publish CI evidence | Story mapping
5 | Implement critical-path CI gates for grounding, trip blocking, evidence integrity, release, and offline idempotency | Executable tests
6 | Add reconciliation and integration-failure observability | Approved configuration and integration contracts
7 | Complete authorization and evidence-retention verification | Approved roles and retention policy
8 | Triage the stale PR and conduct Dev release-readiness review | Current CI gates and traceability

## Slide 7: 5. Release-readiness decision criteria
Do not approve a release beyond Dev until reviewers have evidence that:
the database/persistence decision is approved and implemented consistently;
one authoritative Azure DevOps hierarchy represents each scope item;
critical grounding, trip-block, offline sync, repair/release, and immutable-evidence scenarios pass in CI;
integration failure, retry, escalation, and manual-resolution states are observable and correlated;
authorization prevents unauthorized modification and unauthorized release;
the configured retention and evidence-integrity approach is approved;

## Slide 8: 6. Review decisions requested
Approve or amend the proposed focus on safety, evidence integrity, offline reliability, and operational reconciliation rather than new scope.
Nominate the authoritative Azure DevOps backlog chain and authorize duplicate-item cleanup through closure/linking only.
Resolve the PostgreSQL versus Azure SQL decision with an approved architecture record.
Approve the critical-path CI gate policy after confirming final test thresholds from the complete requirements/NFR baseline.
Confirm the retention, authorized-role, and competent-release policies needed to complete evidence and access-control validation.